## testing score
value predicted | score
value actual

## all task
END TO END MACHINE LEARNING FOR STUDENT CLASSIFICATION PROJECT |  |  | date |  | day |  | SCHEDULE
|  |  |  | start | 8
|  |  |  | duration | 13
role | no | task | date |  |  | status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  |  | start | end | duration (day) |  | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25
[7 empty] | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25
tim prep | 1 | buat formulir berisi nama, kelas, umur, dan tingkat pendidikan (1) | 2023-05-08 | 2023-05-09 | 1 | finish | on duty | pass | off | off | off | off | off | off | off | off | off | off | off | off | off | off | off | off
| 2 | kumpulkan 5 pertanyaan anak kelas 3 sd | 2023-05-08 | 2023-05-09 | 1 | finish | on duty | pass | off | off | off | off | off | off | off | off | off | off | off | off | off | off | off | off
| 3 | kumpulkan 5 pertanyaan anak kelas 6 sd | 2023-05-08 | 2023-05-09 | 1 | finish | on duty | pass | off | off | off | off | off | off | off | off | off | off | off | off | off | off | off | off
| 4 | kumpulkan 5 pertanyaan anak kelas 3 smp | 2023-05-08 | 2023-05-09 | 1 | finish | on duty | pass | off | off | off | off | off | off | off | off | off | off | off | off | off | off | off | off
| 5 | buat tiap pertanyaan memiliki 10 pilihan ganda | 2023-05-08 | 2023-05-09 | 1 | finish | on duty | pass | off | off | off | off | off | off | off | off | off | off | off | off | off | off | off | off
[7 empty] | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25
tim word | 1 | buat semua pertanyaan ke dalam word dokumen | 2023-05-09 | 2023-05-11 | 2 | finish | off | on duty | on duty | pass | off | off | off | off | off | off | off | off | off | off | off | off | off | off
| 2 | jika dokumen melebihi 3 halaman, buat menjadi maksimal 3 halaman | 2023-05-09 | 2023-05-11 | 2 | finish | off | on duty | on duty | pass | off | off | off | off | off | off | off | off | off | off | off | off | off | off
| 3 | print dokumen tersebut menjadi 11 rangkap | 2023-05-11 | 2023-05-12 | 1 | work | off | off | off | on duty | pass | off | off | off | off | off | off | off | off | off | off | off | off | off
| 4 | jilid 1 rangkap dokumen tersebut | 2023-05-11 | 2023-05-12 | 1 | work | off | off | off | on duty | pass | off | off | off | off | off | off | off | off | off | off | off | off | off
| 5 | minta semua list murid regular ycm ke kak kohar | 2023-05-12 | 2023-05-13 | 1 | waiting | off | off | off | off | on duty | pass | off | off | off | off | off | off | off | off | off | off | off | off
| 6 | print list tersebut menjadi 1 lembar yang berisi dua kolom list | 2023-05-12 | 2023-05-13 | 1 | waiting | off | off | off | off | on duty | pass | off | off | off | off | off | off | off | off | off | off | off | off
[7 empty] | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25
tim pencari fakta | 1 | tentukan kapan akan melakukan kuesioner | 2023-05-13 | 2023-05-14 | 1 | waiting | off | off | off | off | off | on duty | pass | off | off | off | off | off | off | off | off | off | off | off
| 2 | minta izin ke core team untuk melakukan kuesioner ke semua murid ycm dalam beberapa batch | 2023-05-13 | 2023-05-14 | 1 | waiting | off | off | off | off | off | on duty | pass | off | off | off | off | off | off | off | off | off | off | off
| 3 | mengumumkan akan ada kuesioner di kelas (2) | 2023-05-15 | 2023-05-17 | 2 | waiting | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off | off | off
| 4 | melakukan absensi dan kalkulasi pembagian batch | 2023-05-15 | 2023-05-17 | 2 | waiting | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off | off | off
| 5 | persiapkan lembar kuesioner dan lembar jawaban | 2023-05-15 | 2023-05-17 | 2 | waiting | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off | off | off
| 6 | persiapkan ruangan untuk melakukan kuesioner | 2023-05-15 | 2023-05-17 | 2 | waiting | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off | off | off
| 7 | melakukan iterasi acak untuk responden | 2023-05-15 | 2023-05-17 | 2 | waiting | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off | off | off
| 8 | membagikan lembar kuesioner dan lembar jawaban | 2023-05-15 | 2023-05-17 | 2 | waiting | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off | off | off
| 9 | instruksi selama 5 menit | 2023-05-15 | 2023-05-17 | 2 | waiting | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off | off | off
| 10 | pengawasan selama 20 menit | 2023-05-15 | 2023-05-17 | 2 | waiting | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off | off | off
| 11 | penutupan | 2023-05-15 | 2023-05-17 | 2 | waiting | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off | off | off
| 12 | merapikan ruangan setelah kuesioner selesai | 2023-05-15 | 2023-05-17 | 2 | waiting | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off | off | off
| 13 | mengumpulkan semua lembar jawaban | 2023-05-15 | 2023-05-17 | 2 | waiting | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off | off | off
[7 empty] | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25
tim database | 1 | membuat dukumen basis data menggunakan spreadsheet | 2023-05-17 | 2023-05-19 | 2 | waiting | off | off | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off
| 2 | melakukan input data lembar hasil | 2023-05-17 | 2023-05-19 | 2 | waiting | off | off | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off
| 3 | melakukan transformasi data menjadi biner data | 2023-05-17 | 2023-05-19 | 2 | waiting | off | off | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off
| 4 | melakukan export data ke dalam csv | 2023-05-17 | 2023-05-19 | 2 | waiting | off | off | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off | off | off
[7 empty] | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25
tim ngoding | 1 | mengambil data csv | 2023-05-19 | 2023-05-21 | 2 | waiting | off | off | off | off | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off
| 2 | melakukan eksplorasi data analis | 2023-05-19 | 2023-05-21 | 2 | waiting | off | off | off | off | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off
| 3 | membuat algoritma machine learning | 2023-05-19 | 2023-05-21 | 2 | waiting | off | off | off | off | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off
| 4 | mengevaluasi algoritma machine learning | 2023-05-19 | 2023-05-21 | 2 | waiting | off | off | off | off | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off
| 5 | membuat layout antarmuka | 2023-05-19 | 2023-05-21 | 2 | waiting | off | off | off | off | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off
| 6 | mengintegrasi website dan machine learning | 2023-05-19 | 2023-05-21 | 2 | waiting | off | off | off | off | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off
| 7 | melakukan deployment ke website streamlit | 2023-05-19 | 2023-05-21 | 2 | waiting | off | off | off | off | off | off | off | off | off | off | off | on duty | on duty | pass | off | off | off | off
keterangan
| 1 | waktu mulai projek | 8
| 2 | waktu untuk memulai survey | 15
Formulas:
date = [date, row above]